## Sheet1
RED LABEL SPOOLS
Quality \ Pressure | 0 /NC | I | II | III
NR | WH | WH | WH | WH
Q1 | WH | WH | WH | WH
Q2 | WH | WH | WH/HOLD | WH/HOLD
Q3 | WH | WH | WH/HOLD | WH/HOLD
Station | WITNESS | HOLD
Work preparation | / | /
pps | / | /
fitting material prep | / | /
pipe material prep | / | /
Cutting | WITNESS | /
cold bending | WITNESS | /
mechanical fabrication | WITNESS | /
Fit up | WITNESS | /
Welding | WITNESS | /
NDT | WITNESS | /
Technical Control | WITNESS | HOLD
Bending Tech Control | WITNESS | HOLD
Station names
Work Preparation
PPS
Fitting Material Preparation
Pipe Material Preparation
Cutting
Mechanical Fabrication
Fitup
Welding
Cold Bending
Induction Bending
NDT
RT
Technical Control
Documentation